## Feuille 1
N° | Description of the risk | Consequences of the risk if it happens | Possible causes | Detectability possible? | Risk evaluation |  |  | Mesures to put in place | New evaluation
[5 empty] | Probability (a) | Severity (b) | Criticality (axb) |  | New probability (a’) | New severity (b’) | New criticality (a’xb’)
1 | Animals (monkeys, birds) | Materials damages | Animals that can interact with the system | Yes | 3 | 3 | 9 | Protection case against external shocks, camouflage | 2 | 1 | 2
2 | Climate deteriorating the system | The system can work badly or even not work at all | Humidity, rain, wind, high temperatures, storm | Yes | 5 | 5 | 25 | Make the protection case thermal insulating and waterproof | 5 | 1 | 5
3 | The system can fall from his place to the ground | Breaking of components, useless pictures | Interaction with animals, wind | Yes | 4 | 5 | 20 | Put movement sensors (to detect the fall), put screw threads on the protection case | 1 | 2 | 2
4 | Overheating of the system | Materials damages | The system operating in a closed case | Yes | 1 | 5 | 5 | Choose components that can work under high temperatures and that don't produce heat | 1 | 1 | 1
5 | Unusable solar panel | Lack of energy | Animals, leaves on the solar panel | Yes | 3 | 3 | 9 | Fix the solar panel to the case, (air blower to clean it ?) | 2 | 2 | 4
6 | Remote communication malfunction | No more communication | Storm, Antenna moved | Yes | 2 | 5 | 10 | Fix the antenna and put it in the protection case | 1 | 5 | 5

## Feuille 2
Probability | Impact |  | Risk level
1 - Rare | 1 - Insignificant
2 - Unlickely | 2 - Minor |  |  | Probability
3 - Possible | 3 - Moderate |  |  | 1 | 2 | 3 | 4 | 5
4 - Probable | 4 - Major | Impact | 5 | 5 | 10 | 15 | 20 | 25
5 - Almost certain | 5 - Catastrophic |  | 4 | 4 | 8 | 12 | 16 | 20
|  |  | 3 | 3 | 6 | 9 | 12 | 15
|  |  | 2 | 2 | 4 | 6 | 8 | 10
|  |  | 1 | 1 | 2 | 3 | 4 | 5
Priority :
|  |  | 1 | Need to fix the problem
|  |  | 2 | Should fix the problem
|  |  | 3 | No problem